## Master Build Tracker
CONNEX — MASTER BUILD TRACKER
# | Phase | Epic | Task | Owner | Priority | Status | Notes
0.1 | Phase 0: Setup | Project Init | Create Expo managed React Native project with TypeScript template | Dev | Critical | Not Started | npx create-expo-app connex --template
0.2 | Phase 0: Setup | Project Init | Create Node.js + Express + TypeScript backend project | Dev | Critical | Not Started | mkdir backend && npm init
0.3 | Phase 0: Setup | Project Init | Set up Supabase project — create DB, enable Auth, Realtime, Storage | Dev | Critical | Not Started | app.supabase.com
0.4 | Phase 0: Setup | Project Init | Create GitHub repo, set up main/dev/feature branch strategy | Dev | Critical | Not Started | Never commit directly to main
0.5 | Phase 0: Setup | Dev Env | Install VS Code extensions (ESLint, Prettier, Tailwind, GitLens) | Dev | High | Not Started | See tech doc Section 3
0.6 | Phase 0: Setup | Dev Env | Configure .env files for mobile (Expo) and backend (Node) | Dev | Critical | Not Started | Never commit .env to GitHub
0.7 | Phase 0: Setup | Dev Env | Set up ESLint + Prettier with project config files | Dev | High | Not Started | Consistent code style
0.8 | Phase 0: Setup | Infrastructure | Create Railway account and link backend project | Dev | High | Not Started | Free tier: $5/month credit
0.9 | Phase 0: Setup | Infrastructure | Create Upstash Redis instance for session caching | Dev | Medium | Not Started | Free tier sufficient for MVP
0.10 | Phase 0: Setup | Infrastructure | Register Firebase project for push notifications (FCM) | Dev | Medium | Not Started | Needed for SOS + chat alerts
1.1 | Phase 1: Auth | Backend | Create users table in Supabase with all required columns | Dev | Critical | Not Started | See DB Schema sheet
1.2 | Phase 1: Auth | Backend | Build POST /auth/register endpoint (phone + password) | Dev | Critical | Not Started | Hash password with bcrypt
1.3 | Phase 1: Auth | Backend | Build legacy /auth/login bridge for pre-Supabase accounts | Dev | Critical | Done | Migrates older custom-auth users into Supabase Auth
1.4 | Phase 1: Auth | Backend | Verify Supabase access tokens on protected routes | Dev | High | Done | Backend auth middleware no longer issues custom JWTs
1.5 | Phase 1: Auth | Backend | Build GET /users/:id — fetch user profile | Dev | High | Not Started | Auth middleware required
1.6 | Phase 1: Auth | Backend | Build PATCH /users/:id — update profile (name, bio, avatar) | Dev | High | Not Started | Validate with Zod
1.7 | Phase 1: Auth | Mobile | Build OnboardingScreen — app intro / value prop slides | Dev | High | Not Started | 3 slides: Chat, Feed, Edu
1.8 | Phase 1: Auth | Mobile | Build RegisterScreen — phone, name, password fields | Dev | Critical | Done | Direct Supabase sign-up using phone/password UI
1.9 | Phase 1: Auth | Mobile | Build LoginScreen — phone + password | Dev | Critical | Done | Direct Supabase login with one-time backend fallback for legacy users
1.10 | Phase 1: Auth | Mobile | Build ProfileSetupScreen — avatar upload + bio | Dev | High | Not Started | Image upload to Supabase Storage
1.11 | Phase 1: Auth | Mobile | Build ProfileScreen (view own) + EditProfileScreen | Dev | High | Not Started
1.12 | Phase 1: Auth | Mobile | Implement Zustand auth store (token, user, isLoggedIn) | Dev | Critical | Not Started | Persisted with AsyncStorage
2.1 | Phase 1: Chat | Backend | Create conversations + conversation_members tables | Dev | Critical | Not Started | See DB Schema sheet
2.2 | Phase 1: Chat | Backend | Create messages table with sender, content, type, status | Dev | Critical | Not Started
2.3 | Phase 1: Chat | Backend | Build POST /chat/conversations — create 1:1 or group chat | Dev | Critical | Not Started
2.4 | Phase 1: Chat | Backend | Build GET /chat/conversations — list user's chats | Dev | Critical | Not Started | Include last message + unread count
2.5 | Phase 1: Chat | Backend | Build POST /chat/messages — send a message | Dev | Critical | Not Started | Broadcast via Supabase Realtime
2.6 | Phase 1: Chat | Backend | Build GET /chat/messages/:convo_id — paginated message history | Dev | High | Not Started | Cursor pagination
2.7 | Phase 1: Chat | Backend | Supabase Realtime channel — subscribe to new messages | Dev | Critical | Not Started | Row Level Security on messages table
2.8 | Phase 1: Chat | Mobile | Build ChatListScreen — list all conversations | Dev | Critical | Not Started | Show avatar, name, last msg, time
2.9 | Phase 1: Chat | Mobile | Build ChatRoomScreen — real-time message view + input | Dev | Critical | Not Started | FlatList inverted + keyboard avoid
2.10 | Phase 1: Chat | Mobile | Build NewChatScreen — search users + start conversation | Dev | High | Not Started
2.11 | Phase 1: Chat | Mobile | Build GroupCreateScreen — name, image, add members | Dev | High | Not Started
2.12 | Phase 1: Chat | Mobile | Implement message status: sent / delivered / read receipts | Dev | High | Not Started | Double tick logic
2.13 | Phase 1: Chat | Mobile | Build StatusListScreen + StatusViewScreen (24h stories) | Dev | Medium | Not Started | Supabase Storage for status media
3.1 | Phase 1: SOS | Backend | Create sos_contacts + sos_events tables | Dev | Critical | Not Started | Mutual consent required
3.2 | Phase 1: SOS | Backend | Build POST /sos/contacts — add emergency contact (requires accept) | Dev | Critical | Not Started | Notify contact via FCM
3.3 | Phase 1: SOS | Backend | Build POST /sos/contacts/:id/accept — accept SOS contact request | Dev | Critical | Not Started
3.4 | Phase 1: SOS | Backend | Build POST /sos/trigger — trigger SOS event | Dev | Critical | Not Started | Notify all accepted contacts via FCM
3.5 | Phase 1: SOS | Backend | Build POST /sos/cancel — cancel active SOS event | Dev | High | Not Started | Notify contacts that user is safe
3.6 | Phase 1: SOS | Mobile | Build SOSScreen — press-and-hold button (3s activation) | Dev | Critical | Not Started | Haptic feedback + countdown
3.7 | Phase 1: SOS | Mobile | Build SOSContactsScreen — manage emergency contacts | Dev | High | Not Started | Pending / accepted states
3.8 | Phase 1: SOS | Mobile | Handle incoming SOS push notification (alert banner) | Dev | Critical | Not Started | Wake screen if app in background
4.1 | Phase 1: Feed | Backend | Create posts + post_reactions + follows tables | Dev | Critical | Not Started
4.2 | Phase 1: Feed | Backend | Build POST /feed/posts — create post (text/image + optional alert_tag) | Dev | Critical | Not Started | alert_tag: Utility/Safety/Traffic/Water/Weather/Community
4.3 | Phase 1: Feed | Backend | Build GET /feed/posts — paginated home feed (following + local) | Dev | Critical | Not Started | Cursor pagination
4.4 | Phase 1: Feed | Backend | Build GET /feed/posts/alerts — filter by alert_tag + area_id | Dev | Critical | Not Started | Powers the Alerts tab
4.5 | Phase 1: Feed | Backend | Build POST /feed/reactions — like/react to a post | Dev | High | Not Started
4.6 | Phase 1: Feed | Backend | Build POST /feed/follow + DELETE /feed/follow — follow/unfollow | Dev | High | Not Started
4.7 | Phase 1: Feed | Mobile | Build FeedHomeScreen — scrollable post feed | Dev | Critical | Not Started | Tab: For You / Following
4.8 | Phase 1: Feed | Mobile | Build AlertsTabScreen — filter by 6 alert categories | Dev | Critical | Not Started | Category chips: All/Utility/Safety/Traffic/Water/Weather/Community
4.9 | Phase 1: Feed | Mobile | Build CreatePostScreen — text + image + alert tag picker | Dev | High | Not Started | Image from camera or gallery
4.10 | Phase 1: Feed | Mobile | Build PostDetailScreen — post + reactions + comments thread | Dev | High | Not Started
4.11 | Phase 1: Feed | Mobile | Build ExploreScreen — search users and posts | Dev | Medium | Not Started
5.1 | Phase 1: Alerts | Backend | Create loadshedding_schedules table | Dev | Critical | Not Started
5.2 | Phase 1: Alerts | Backend | Build EskomSePush integration — fetch schedule by suburb | Dev | Critical | Not Started | 50 free API calls/day — cache aggressively
5.3 | Phase 1: Alerts | Backend | Cron job: refresh loadshedding data every 4 hours | Dev | High | Not Started | node-cron + Redis cache
5.4 | Phase 1: Alerts | Backend | Build GET /alerts/loadshedding?suburb=x — serve cached data | Dev | High | Not Started
5.5 | Phase 1: Alerts | Mobile | Build AlertsMapScreen — show user's local alerts on map | Dev | Medium | Not Started | react-native-maps
6.1 | Phase 1: Edu | Backend | Create edu_papers table (subject, grade, year, url) | Dev | High | Not Started
6.2 | Phase 1: Edu | Backend | Seed DBE past papers (Grades 10-12, last 5 years) | Dev | High | Not Started | PDFs stored in Supabase Storage
6.3 | Phase 1: Edu | Backend | Build GET /edu/papers?grade=x&subject=y — filter papers | Dev | High | Not Started
6.4 | Phase 1: Edu | Mobile | Build EduHomeScreen — grade selector + subject grid | Dev | High | Not Started
6.5 | Phase 1: Edu | Mobile | Build PaperListScreen — list papers by subject + year | Dev | High | Not Started
6.6 | Phase 1: Edu | Mobile | Build PaperViewerScreen — in-app PDF viewer | Dev | High | Not Started | react-native-pdf
7.1 | Phase 1: Final | QA | Manual test: full auth flow (register, login, logout) | QA | Critical | Not Started | See Testing sheet
7.2 | Phase 1: Final | QA | Manual test: send/receive messages in real time | QA | Critical | Not Started
7.3 | Phase 1: Final | QA | Manual test: SOS trigger + contact notification | QA | Critical | Not Started
7.4 | Phase 1: Final | QA | Manual test: create post with alert tag — appears in Alerts tab | QA | Critical | Not Started
7.5 | Phase 1: Final | QA | Manual test: download + view past paper PDF | QA | High | Not Started
7.6 | Phase 1: Final | Deployment | Deploy backend to Railway — set production env vars | Dev | Critical | Not Started
7.7 | Phase 1: Final | Deployment | Build mobile app with Expo EAS — internal distribution APK | Dev | Critical | Not Started | For investor demo devices
7.8 | Phase 1: Final | Deployment | Register for Google Play Console ($25 one-time fee) | Founder | High | Not Started | Needed before public launch

## Screen Inventory
CONNEX — SCREEN INVENTORY
Screen Name | Navigator | Section | File Path | Auth Required | Phase | Notes
OnboardingScreen | Root Stack | Auth | src/screens/auth/OnboardingScreen.tsx | No | 1 | App intro slides — shown once
RegisterScreen | Auth Stack | Auth | src/screens/auth/RegisterScreen.tsx | No | 1 | Phone + name + password
LoginScreen | Auth Stack | Auth | src/screens/auth/LoginScreen.tsx | No | 1 | Phone + password
ProfileSetupScreen | Auth Stack | Auth | src/screens/auth/ProfileSetupScreen.tsx | No | 1 | Post-register: avatar + bio
ChatListScreen | Chat Stack | Chat | src/screens/chat/ChatListScreen.tsx | Yes | 1 | All conversations
ChatRoomScreen | Chat Stack | Chat | src/screens/chat/ChatRoomScreen.tsx | Yes | 1 | Real-time message thread
NewChatScreen | Chat Stack | Chat | src/screens/chat/NewChatScreen.tsx | Yes | 1 | Search users, start convo
GroupCreateScreen | Chat Stack | Chat | src/screens/chat/GroupCreateScreen.tsx | Yes | 1 | Name + image + add members
StatusListScreen | Chat Stack | Chat | src/screens/chat/StatusListScreen.tsx | Yes | 1 | WhatsApp-style status list
StatusViewScreen | Chat Stack | Chat | src/screens/chat/StatusViewScreen.tsx | Yes | 1 | Full-screen status view
SOSScreen | Chat Stack | SOS | src/screens/sos/SOSScreen.tsx | Yes | 1 | Press-hold 3s activation
SOSContactsScreen | Chat Stack | SOS | src/screens/sos/SOSContactsScreen.tsx | Yes | 1 | Manage emergency contacts
FeedHomeScreen | Feed Stack | Feed | src/screens/feed/FeedHomeScreen.tsx | Yes | 1 | Home feed + Following tab
AlertsTabScreen | Feed Stack | Alerts | src/screens/feed/AlertsTabScreen.tsx | Yes | 1 | 6 alert category filters
AlertsMapScreen | Feed Stack | Alerts | src/screens/feed/AlertsMapScreen.tsx | Yes | 1 | Map view of local alerts
CreatePostScreen | Feed Stack | Feed | src/screens/feed/CreatePostScreen.tsx | Yes | 1 | Text + image + alert tag
PostDetailScreen | Feed Stack | Feed | src/screens/feed/PostDetailScreen.tsx | Yes | 1 | Post + comments + reactions
ExploreScreen | Feed Stack | Feed | src/screens/feed/ExploreScreen.tsx | Yes | 1 | Search users and posts
EduHomeScreen | Edu Stack | Edu | src/screens/edu/EduHomeScreen.tsx | Yes | 1 | Grade selector + subject grid
PaperListScreen | Edu Stack | Edu | src/screens/edu/PaperListScreen.tsx | Yes | 1 | Papers by subject + year
PaperViewerScreen | Edu Stack | Edu | src/screens/edu/PaperViewerScreen.tsx | Yes | 1 | In-app PDF viewer
ProfileScreen | Profile Stack | Profile | src/screens/profile/ProfileScreen.tsx | Yes | 1 | View own or other user profile
EditProfileScreen | Profile Stack | Profile | src/screens/profile/EditProfileScreen.tsx | Yes | 1 | Edit name, bio, avatar
SettingsScreen | Profile Stack | Settings | src/screens/profile/SettingsScreen.tsx | Yes | 1 | App settings + logout
NotificationsScreen | Root Stack | System | src/screens/NotificationsScreen.tsx | Yes | 1 | Push notification history
PayHomeScreen | Pay Stack | Pay | src/screens/pay/PayHomeScreen.tsx | Yes | 2 | Phase 2: Connex Pay wallet
SendMoneyScreen | Pay Stack | Pay | src/screens/pay/SendMoneyScreen.tsx | Yes | 2 | Phase 2: P2P transfer
ClipsHomeScreen | Clips Stack | Clips | src/screens/clips/ClipsHomeScreen.tsx | Yes | 3 | Phase 3: Short-form video feed
LogisticsHomeScreen | Logistics Stack | Logistics | src/screens/logistics/LogisticsHomeScreen.tsx | Yes | 4 | Phase 4: Ride/delivery/parcels

## API Endpoints
CONNEX — API ENDPOINTS
Method | Endpoint | Group | Description | Auth | Phase | Notes
POST | /auth/register | Auth | Register new user (phone, name, password) | No | 1 | Hash pw with bcrypt
POST | /auth/login | Auth | Legacy-account bridge into Supabase Auth sessions | No | 1 | Only needed for pre-migration users
POST | /auth/logout | Auth | Revoke current Supabase session from backend if needed | Yes | 1
POST | /auth/refresh | Auth | Refresh Supabase session using refresh token | No | 1
GET | /users/:id | Users | Get user profile by ID | Yes | 1
PATCH | /users/:id | Users | Update profile (name, bio, avatar_url) | Yes | 1 | Own profile only
GET | /users/search?q=x | Users | Search users by name or phone | Yes | 1 | For NewChatScreen
POST | /chat/conversations | Chat | Create new conversation (1:1 or group) | Yes | 1
GET | /chat/conversations | Chat | List all conversations for auth user | Yes | 1 | Includes last msg + unread count
GET | /chat/conversations/:id | Chat | Get single conversation details + members | Yes | 1
PATCH | /chat/conversations/:id | Chat | Update group name or image | Yes | 1 | Group admin only
POST | /chat/conversations/:id/members | Chat | Add member to group conversation | Yes | 1
DELETE | /chat/conversations/:id/members/:uid | Chat | Remove member from group | Yes | 1
POST | /chat/messages | Chat | Send a message in a conversation | Yes | 1 | Triggers Realtime broadcast
GET | /chat/messages/:convo_id | Chat | Get paginated message history (cursor-based) | Yes | 1
PATCH | /chat/messages/:id/read | Chat | Mark message as read (update status) | Yes | 1
POST | /feed/posts | Feed | Create post (text, image_url, optional alert_tag) | Yes | 1 | alert_tag triggers Alerts tab
GET | /feed/posts | Feed | Paginated home feed (following + area) | Yes | 1 | Cursor pagination
GET | /feed/posts/alerts | Feed | Get alert posts — filter by tag + area_id | Yes | 1 | Powers Alerts tab
GET | /feed/posts/:id | Feed | Get single post with reactions + comments | Yes | 1
DELETE | /feed/posts/:id | Feed | Delete own post | Yes | 1
POST | /feed/reactions | Feed | Like or react to a post | Yes | 1
DELETE | /feed/reactions/:post_id | Feed | Remove reaction from post | Yes | 1
POST | /feed/follow | Feed | Follow a user | Yes | 1
DELETE | /feed/follow/:user_id | Feed | Unfollow a user | Yes | 1
GET | /alerts/loadshedding | Alerts | Get loadshedding schedule for suburb (cached) | Yes | 1 | ?suburb=x Query param required
GET | /alerts/loadshedding/stage | Alerts | Get current national loadshedding stage | Yes | 1 | Updated every 30min
POST | /sos/contacts | SOS | Add emergency contact (sends accept request) | Yes | 1 | Mutual consent required
GET | /sos/contacts | SOS | List own SOS contacts (pending + accepted) | Yes | 1
POST | /sos/contacts/:id/accept | SOS | Accept incoming SOS contact request | Yes | 1
DELETE | /sos/contacts/:id | SOS | Remove emergency contact | Yes | 1
POST | /sos/trigger | SOS | Trigger SOS event — notify all accepted contacts | Yes | 1 | FCM push to all contacts
POST | /sos/cancel | SOS | Cancel active SOS — notify contacts user is safe | Yes | 1
GET | /sos/events | SOS | Get SOS event history | Yes | 1
GET | /edu/papers | Edu | Get papers — filter by grade, subject, year | Yes | 1 | ?grade=12&subject=Maths&year=2023
GET | /edu/papers/:id | Edu | Get single paper metadata + download URL | Yes | 1 | Signed Supabase Storage URL
GET | /edu/subjects | Edu | List all available subjects | Yes | 1
GET | /edu/grades | Edu | List available grades (10, 11, 12) | Yes | 1
POST | /pay/wallet | Pay | Create Connex Pay wallet for user | Yes | 2 | Phase 2
POST | /pay/transfer | Pay | P2P money transfer between users | Yes | 2 | Phase 2
GET | /pay/transactions | Pay | Get transaction history | Yes | 2 | Phase 2

## Database Schema
CONNEX — DATABASE SCHEMA (Supabase / PostgreSQL)
Table | Column | Type | Nullable | Default / FK | Index | Notes
users | id | UUID | No | gen_random_uuid() | PK | Primary key
users | phone | VARCHAR(20) | No | UNIQUE | UNIQUE | E.164 format: +27...
users | name | VARCHAR(100) | No |  |  | Display name
users | bio | TEXT | Yes
users | avatar_url | TEXT | Yes |  |  | Supabase Storage URL
users | area_id | VARCHAR(50) | Yes |  | INDEX | Township / suburb identifier
users | province | VARCHAR(50) | Yes |  |  | e.g. Gauteng
users | is_active | BOOLEAN | No | true |  | Soft disable account
users | created_at | TIMESTAMPTZ | No | now()
users | updated_at | TIMESTAMPTZ | No | now()
conversations | id | UUID | No | gen_random_uuid() | PK
conversations | type | VARCHAR(10) | No | 'direct' |  | direct ¦ group
conversations | name | VARCHAR(100) | Yes |  |  | Group name (null for direct)
conversations | image_url | TEXT | Yes |  |  | Group avatar
conversations | created_by | UUID | No | FK → users.id | FK
conversations | created_at | TIMESTAMPTZ | No | now()
conversation_members | id | UUID | No | gen_random_uuid() | PK
conversation_members | conversation_id | UUID | No | FK → conversations.id | FK | CASCADE DELETE
conversation_members | user_id | UUID | No | FK → users.id | FK
conversation_members | role | VARCHAR(10) | No | 'member' |  | member ¦ admin
conversation_members | joined_at | TIMESTAMPTZ | No | now()
conversation_members | last_read_at | TIMESTAMPTZ | Yes |  |  | For unread count calc
messages | id | UUID | No | gen_random_uuid() | PK
messages | conversation_id | UUID | No | FK → conversations.id | FK+IDX
messages | sender_id | UUID | No | FK → users.id | FK
messages | content | TEXT | Yes |  |  | Null for media-only
messages | type | VARCHAR(20) | No | 'text' |  | text¦image¦video¦audio¦system
messages | media_url | TEXT | Yes |  |  | Supabase Storage URL
messages | status | VARCHAR(20) | No | 'sent' |  | sent¦delivered¦read
messages | created_at | TIMESTAMPTZ | No | now() | IDX | Sort order
sos_contacts | id | UUID | No | gen_random_uuid() | PK
sos_contacts | user_id | UUID | No | FK → users.id | FK | Who added the contact
sos_contacts | contact_id | UUID | No | FK → users.id | FK | The emergency contact
sos_contacts | status | VARCHAR(20) | No | 'pending' |  | pending¦accepted¦rejected
sos_contacts | created_at | TIMESTAMPTZ | No | now()
sos_events | id | UUID | No | gen_random_uuid() | PK
sos_events | user_id | UUID | No | FK → users.id | FK | Who triggered SOS
sos_events | status | VARCHAR(20) | No | 'active' |  | active¦cancelled¦resolved
sos_events | latitude | FLOAT | Yes |  |  | Phase 2: live location
sos_events | longitude | FLOAT | Yes |  |  | Phase 2: live location
sos_events | triggered_at | TIMESTAMPTZ | No | now() | IDX
sos_events | resolved_at | TIMESTAMPTZ | Yes
posts | id | UUID | No | gen_random_uuid() | PK
posts | author_id | UUID | No | FK → users.id | FK
posts | content | TEXT | Yes
posts | image_url | TEXT | Yes |  |  | Supabase Storage URL
posts | alert_tag | VARCHAR(20) | Yes | NULL | IDX | Utility¦Safety¦Traffic¦Water¦Weather¦Community
posts | area_id | VARCHAR(50) | Yes |  | IDX | Inherited from user.area_id at post time
posts | is_deleted | BOOLEAN | No | false |  | Soft delete
posts | created_at | TIMESTAMPTZ | No | now() | IDX
post_reactions | id | UUID | No | gen_random_uuid() | PK
post_reactions | post_id | UUID | No | FK → posts.id | FK | CASCADE DELETE
post_reactions | user_id | UUID | No | FK → users.id | FK
post_reactions | type | VARCHAR(20) | No | 'like' |  | like¦love¦support¦alert
post_reactions | created_at | TIMESTAMPTZ | No | now()
follows | id | UUID | No | gen_random_uuid() | PK
follows | follower_id | UUID | No | FK → users.id | FK | Who is following
follows | following_id | UUID | No | FK → users.id | FK | Who is being followed
follows | created_at | TIMESTAMPTZ | No | now()
loadshedding_schedules | id | UUID | No | gen_random_uuid() | PK
loadshedding_schedules | suburb_id | VARCHAR(50) | No |  | IDX | EskomSePush suburb ID
loadshedding_schedules | suburb_name | VARCHAR(100) | No
loadshedding_schedules | stage | INTEGER | No | 0 |  | Current national stage
loadshedding_schedules | schedule | JSONB | No | '{}' |  | Full schedule JSON from ESP
loadshedding_schedules | fetched_at | TIMESTAMPTZ | No | now() | IDX | Last API fetch time
edu_papers | id | UUID | No | gen_random_uuid() | PK
edu_papers | subject | VARCHAR(100) | No |  |  | e.g. Mathematics
edu_papers | grade | INTEGER | No |  | IDX | 10, 11, or 12
edu_papers | year | INTEGER | No |  | IDX | e.g. 2023
edu_papers | paper_num | INTEGER | Yes | 1 |  | 1, 2, or 3 where applicable
edu_papers | language | VARCHAR(20) | No | 'English' |  | English¦Afrikaans
edu_papers | type | VARCHAR(20) | No | 'question' |  | question¦memo
edu_papers | storage_url | TEXT | No |  |  | Supabase Storage path
edu_papers | created_at | TIMESTAMPTZ | No | now()

## Dependencies
CONNEX — DEPENDENCIES & PACKAGES
Package | Version | Location | Purpose | Install Command | Notes
expo | ~52.x | Mobile | Core Expo managed framework | npx create-expo-app
react-native | 0.76.x | Mobile | Core mobile framework | Bundled with Expo
typescript | ^5.x | Mobile | Static type checking | Bundled with template
@react-navigation/native | ^6.x | Mobile | Navigation container | npx expo install
@react-navigation/stack | ^6.x | Mobile | Stack navigator (auth flow) | npx expo install
@react-navigation/bottom-tabs | ^6.x | Mobile | Bottom tab bar navigator | npx expo install
zustand | ^5.x | Mobile | Lightweight global state management | npm install zustand
nativewind | ^4.x | Mobile | Tailwind CSS for React Native | npm install nativewind
tailwindcss | ^3.x | Mobile | Tailwind config (NativeWind peer) | npm install tailwindcss
@supabase/supabase-js | ^2.x | Mobile | Supabase client (auth, DB, Realtime) | npm install @supabase/supabase-js
expo-notifications | ~0.29.x | Mobile | Push notification handling | npx expo install | Works with FCM
expo-image-picker | ~16.x | Mobile | Pick images from gallery / camera | npx expo install
expo-file-system | ~18.x | Mobile | File access for PDF download | npx expo install
expo-haptics | ~14.x | Mobile | Haptic feedback for SOS hold button | npx expo install
react-native-maps | ^1.x | Mobile | Map view for Alerts screen | npx expo install
react-native-pdf | ^6.x | Mobile | In-app PDF viewer for Edu | npm install react-native-pdf
@react-native-async-storage/async-storage | ^2.x | Mobile | Persist Zustand auth store | npx expo install
dayjs | ^1.x | Mobile | Date/time formatting | npm install dayjs | Lightweight moment.js alternative
zod | ^3.x | Mobile | Runtime schema validation | npm install zod | Shared with backend
express | ^4.x | Backend | HTTP server framework | npm install express
typescript | ^5.x | Backend | Static type checking | npm install -D typescript
ts-node | ^10.x | Backend | Run TS directly in dev | npm install -D ts-node
nodemon | ^3.x | Backend | Auto-restart on file change | npm install -D nodemon
@supabase/supabase-js | ^2.x | Backend | Supabase admin client | npm install @supabase/supabase-js | Use service_role key
bcryptjs | ^3.x | Backend | Legacy-password migration support | npm install bcryptjs | Used only to migrate older custom-auth users
zod | ^3.x | Backend | Request body validation | npm install zod
ioredis | ^5.x | Backend | Redis client for Upstash | npm install ioredis
node-cron | ^3.x | Backend | Scheduled jobs (loadshedding refresh) | npm install node-cron
axios | ^1.x | Backend | HTTP client for EskomSePush API | npm install axios
cors | ^2.x | Backend | CORS middleware | npm install cors
helmet | ^8.x | Backend | Security headers middleware | npm install helmet
express-rate-limit | ^7.x | Backend | Rate limiting for auth endpoints | npm install express-rate-limit
dotenv | ^16.x | Backend | Load .env files | npm install dotenv
firebase-admin | ^12.x | Backend | Send FCM push notifications | npm install firebase-admin
multer | ^1.x | Backend | File upload handling | npm install multer | For image uploads
uuid | ^9.x | Backend | Generate UUIDs (if not using Supabase) | npm install uuid

## Phase Roadmap
CONNEX — PHASE ROADMAP & BUSINESS MILESTONES
Phase | Name | Key Features | Monetization | Target ARR | Timeline | Status
0 | Setup & Architecture | Project init, Supabase setup, GitHub repo, dev environment, folder structure, CI skeleton | No revenue — build foundation | R0 | Weeks 1–2 | Not Started
1 | MVP: Chat + Feed + Edu | Chat (real-time, groups, WhatsApp-style status) SOS button (press-hold, FCM alerts to contacts, mutual consent) Feed (posts, reactions, follows) Alerts tab (6 categories, self-tagged + EskomSePush) Edu (DBE past papers, in-app PDF viewer) | No direct revenue Focus: User acquisition, organic growth, investor demo readiness | R0 (pre-revenue) | Weeks 3–14 | Not Started
2 | Connex Pay | In-app digital wallet P2P money transfers (phone-to-phone) QR code payments Transaction history Bill pay (electricity, data, DSTV) Regulatory: SARB compliance pathway | Transaction fees (1–2%) Float interest income Business payment acceptance fee Connex Premium subscription launch | R35M/yr at scale | Month 4–8 | Not Started
3 | Connex Clips | Short-form vertical video feed (TikTok-style) Record in-app or upload Audio overlay, filters, text Discover feed (algorithm) Creator profiles Live streaming (Phase 3B) | Video ads (mid-roll, sponsored) Creator monetization share Boosted content / promoted clips Brand partnerships with local SA brands | R15M/yr | Month 9–14 | Not Started
4 | Connex Logistics | Ride-hailing (Uber-equivalent, township-first pricing) Food delivery (local restaurants + township traders) Parcel delivery (person-to-person, SME fulfilment) Grocery delivery Connex for Business (SME merchant dashboard) Driver/courier partner app | Commission per trip/order (15–25%) Subscription: Connex Business tier Surge pricing (peak hours) Delivery insurance upsell White-label logistics API for enterprises | R68M/yr at scale | Month 15–24 | Not Started
5+ | Connex Enterprise & Expansion | Multi-country expansion (Zimbabwe, Nigeria, Kenya, Ghana) Connex Data & API licensing (anonymised community data) Government & NGO integrations (civic alerts, healthcare) Connex for Schools (Edu premium) SAPS / emergency services SOS integration | Data licensing Government contracts Enterprise API access Franchise/partner model per country | R180M+/yr | Year 3–5 | Not Started

## Integration Tracker
CONNEX — THIRD-PARTY INTEGRATION TRACKER
Service | Type | Used For | Free Tier | Cost at Scale | Phase | Status | Docs / Notes
Supabase | BaaS | DB (PostgreSQL), Auth, Realtime (chat), Storage (media/PDFs) | 500MB DB, 1GB storage, 50k MAU | Pro: $25/month | 1 | Not Started | supabase.com — use service_role key on backend only
Railway | Hosting | Node.js backend deployment + auto SSL | $5/month credit (free to start) | ~$10–30/month (scales with usage) | 1 | Not Started | railway.app — connect GitHub repo for auto-deploy
Upstash Redis | Cache / KV | Optional cache, rate limiting, loadshedding data cache | 10k commands/day free | Pay-per-use: very cheap | 1 | Optional | upstash.com — enable only when in-memory fallback is no longer enough
Firebase FCM | Push Notifications | SOS alerts, chat notifications, feed mentions | Unlimited push (free) | Free — no cost for FCM | 1 | Not Started | console.firebase.google.com — use Admin SDK on backend
Expo EAS | Build & Deploy | Build APK/AAB, OTA updates, internal distribution | Free for personal (30 builds/month) | Production: $99/month | 1 | Not Started | expo.dev — use eas build --profile preview for investor APK
EskomSePush API | Data Feed | Official loadshedding schedule + stage data | 50 free API calls/day | Paid tier: R999+/month | 1 | Not Started | eskomsepush.app — cache AGGRESSIVELY in Redis to stay in free tier
Google Play Console | App Distribution | Publish Android app to Play Store | $25 one-time dev registration fee | $25 once (no monthly fee) | 1 | Not Started | play.google.com/console — register before alpha test on device
Apple App Store | App Distribution | Publish iOS app to App Store | None — $99/year required | $99/year developer account | 1 | Not Started | developer.apple.com — MVP can be Android-only initially
Cloudinary | Media CDN | Image/video optimisation and CDN delivery (optional fallback) | 25GB storage, 25GB bandwidth/month | $89/month (Plus) | 1 | Not Started | Alternative to Supabase Storage for heavy media — Phase 3+
OpenWeatherMap API | Data Feed | Weather alerts for Alerts tab | 1000 calls/day free | Professional: $40/month | 2 | Not Started | openweathermap.org — Phase 2 addition to alerts
Flutterwave | Payments | ZAR card payments, bank transfers for Connex Pay | No monthly fee (per-transaction) | 2.9% + R1.50 per transaction | 2 | Not Started | flutterwave.com — SA-registered business required
Paystack | Payments | Alternative SA payment gateway for Connex Pay | No setup fee | 1.5% per transaction (cap R2000) | 2 | Not Started | paystack.com — also owned by Stripe, solid SA coverage
AWS S3 / Rekognition | AI/Storage | Video storage for Clips + content moderation | 5GB S3 free 12 months | $0.023/GB/month storage | 3 | Not Started | Phase 3 — scale media beyond Supabase Storage
Google Maps Platform | Mapping | Ride-hailing routing, driver tracking, ETA calculation | $300/month credit (90-day) | $0.005 per request at scale | 4 | Not Started | Phase 4 — required for logistics
Twilio | Comms | OTP SMS verification (phone number auth) | Trial credit $15 | ~$0.0075 per SMS | 1 | Not Started | Alternative: Supabase Auth built-in OTP (use this first)
Sentry | Monitoring | Error tracking for mobile + backend | 5k errors/month free | Team: $26/month | 1 | Not Started | sentry.io — essential for production crash tracking
PostHog | Analytics | Product analytics, user funnels, session recording | 1M events/month free | Scale: $450/month | 1 | Not Started | posthog.com — open source, POPIA-friendly